## Agile Project Plan
| Project Name | Design and Development of a Department-Level Capstone Repository with Similarity Analysis and Recommendation Support |  |  | Start Date | End Date | Overall Progress | Project Deliverable
| Project Manager | Manuel, Hailey Joel B. |  |  | 2025-12-12 |  |  | Scope Statement
At Risk | Task Name | Feature Type | Responsible | Checkpoints | Start | Finish | Duration in days | Status | Comments
| Sprint 1 | Conceptualization | Team |  | 2025-12-12 | 2026-01-19 | 39 | Complete
No | Identify Project Topic | Conceptualization | Team | Brainstorm and Select Ideas | 2025-12-12 | 2026-01-19 | 39 | Complete
| Sprint 2 | Planning | Team |  | 2026-01-19 | 2026-02-06 | 19
No | Requirement Gathering | Planning | Team | Identify users and functions | 2026-01-19 | 2026-02-06 | 19 | Complete
| Sprint 3 | Documentation & Design | Team |  | 2026-01-26 | 2026-04-13 | 78
No | Write Chapter 1 | Documentation | Team | Draft -> Revise -> Finalize | 2026-01-26 | 2026-04-13 | 78 | Needs Review
Yes | Create Diagrams | Documentation | Team | DFD, Use case, ERD | 2026-02-23 | 2026-04-10 | 47 | Complete
Yes | Write Chapter 2 | Documentation | Team | Draft -> Revise -> Finalize | 2026-03-30 | 2026-04-13 | 15 | Needs Review
No | UI/UX Planning | Design | Team | Pages, Flows and Layout | 2026-04-10 | 2026-04-11 | 2 | Complete
No | Create Wireframes | Design | Team | Review Layout | 2026-04-11 | 2026-04-11 | 1 | Complete
No | Design UI Mockups | Design | Team | Colors, Components, Layouts | 2026-04-12 | 2026-04-12 | 1 | Complete
No | Create Interface Prototype | Prototyping | Team | Links, Navigations, Testing | 2026-04-13 | 2026-04-13 | 1 | Complete
8
Formulas:
Start Date = MIN([Start Date, row below]:[Start Date, row below])
Start Date = MIN([Start Date, row below]:G18)
End Date = MAX([End Date, row below]:[End Date, row below])
End Date = MAX([End Date, row below]:H18)

## Example of Agile Project Plan
Agile Project Plan Template
| Project Name | New Product Launch |  |  | Start Date | End Date | Overall Progress | Project Deliverable | Launch-ready product with core features, documentation, and release plan
| Project Manager | Cyriac Tom |  |  | 2026-01-01 | 2026-02-14 | 83% | Scope Statement | Deliver a stable MVP through three sprints, covering core features, testing, stakeholder review, and launch readiness
At Risk | Task Name | Feature Type | Responsible | Checkpoints | Start | Finish | Duration in days | Status | Comments
No | Sprint 1 | Sprint | Product Team | Sprint Planning Completed | 2026-01-01 | 2026-01-12 | 12 | In Progress | Initial sprint setup and backlog alignment
Yes | Feature 1 | Core Feature | Dev Team | Development Complete | 2026-01-01 | 2026-01-07 | 7 | Complete | Ready for QA validation
No | Feature 2 | Enhancement | Dev Team | Partial Build Done | 2026-01-03 | 2026-01-10 | 8 | On Hold | Waiting for dependency approval
No | Feature 3 | Core Feature | QA Team | Test Cases Prepared | 2026-01-05 | 2026-01-12 | 8 | Needs Review | Requires stakeholder feedback
No | Sprint 2 | Sprint | Product Team | Sprint Review Scheduled | 2026-01-15 | 2026-01-28 | 14 | Approved | Scope and priorities confirmed
No | Feature 4 | Core Feature | Dev Team | Code Review Done | 2026-01-15 | 2026-01-15 | 1 | Complete | Merged into main branch
Yes | Feature 5 | Enhancement | QA Team | Testing Delayed | 2026-01-16 | 2026-01-25 | 10 | Overdue | Blocked due to resource availability
No | Feature 6 | Support Feature | Dev Team | Development Paused | 2026-01-18 | 2026-01-28 | 11 | On Hold | Re-prioritised for next sprint
No | Sprint 3 | Sprint | Product Team | Sprint Review Pending | 2026-01-29 | 2026-02-14 | 17 | Needs Review | Final adjustments required
No | Feature 7 | Core Feature | Dev Team | Build Completed | 2026-01-29 | 2026-02-05 | 8 | Complete | Ready for release testing
No | Feature 8 | Enhancement | QA Team | Regression Testing | 2026-02-01 | 2026-02-08 | 8 | In Progress | Minor issues under review
Yes | Feature 9 | Release Prep | Product + Ops | Go-Live Checklist | 2026-02-05 | 2026-02-14 | 10 | Not Started | Scheduled for final phase
Formulas:
Start Date = MIN([Start Date, row below]:G9)
End Date = MAX([End Date, row below]:H9)

## Dropdown Keys - Do Not Delete -
Dropdown Keys
Yes / No | Priority | Status
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold