## Agile Project Plan
| Project Name | Design and Development of a Department-Level Capstone Repository with Similarity Analysis and Recommendation Support |  |  | Start Date | End Date | Overall Progress | Project Deliverable | Tested department-level capstone repository with similarity analysis, role-based access, archive management, and documentation.
| Project Manager | Manuel, Hailey Joel B. |  |  | 2025-12-12 | 2026-09-21 | 81.71% | Scope Statement | Complete the implementation, validation, documentation, and deployment readiness of CAPRE.
At Risk | Task Name | Feature Type | Responsible | Checkpoints | Start | Finish | Duration in days | Status | Comments
No | Sprint 1 | Sprint | Team |  | 2025-12-12 | 2026-01-19 | 39 | Complete
No | Identify Project Topic | Conceptualization | Team | Brainstorm and select project topic | 2025-12-12 | 2026-01-19 | 39 | Complete | Historical conceptualization completed.
No | Sprint 2 | Sprint | Team |  | 2026-01-19 | 2026-02-06 | 19 | Complete
No | Requirement Gathering | Planning | Team | Identify users and system functions | 2026-01-19 | 2026-02-06 | 19 | Complete | Historical requirements work completed.
No | Sprint 3 | Sprint | Team |  | 2026-01-26 | 2026-04-13 | 78 | Complete
No | Write Chapter 1 | Documentation | Team | Draft → Revise → Finalize | 2026-01-26 | 2026-04-13 | 78 | Complete | Historical draft retained; pending final review.
No | Create Diagrams | Documentation | Team | DFD, Use Case, and ERD | 2026-02-23 | 2026-04-10 | 47 | Complete | Core system diagrams completed.
No | Write Chapter 2 | Documentation | Team | Draft → Revise → Finalize | 2026-03-30 | 2026-04-13 | 15 | Complete | Historical draft retained; pending final review.
No | UI/UX Planning | Design | Team | Define pages, flows, and layout | 2026-04-10 | 2026-04-11 | 2 | Complete | UI/UX planning completed.
No | Create Wireframes | Design | Team | Review page layout | 2026-04-11 | 2026-04-11 | 1 | Complete | Wireframes completed.
No | Design UI Mockups | Design | Team | Finalize colors, components, and layouts | 2026-04-12 | 2026-04-12 | 1 | Complete | UI mockups completed.
No | Create Interface Prototype | Prototyping | Team | Link navigation and test prototype | 2026-04-13 | 2026-04-13 | 1 | Complete | Clickable prototype completed.
No | Sprint 4 | Sprint | Team |  | 2026-04-26 | 2026-05-15 | 20 | Complete
No | Project scaffolding and route architecture | Development | Team | Establish application structure and route modules | 2026-04-26 | 2026-05-12 | 17 | Complete | Core Flask project structure and routing implemented.
No | Signup, sign-in, and user management | Authentication | Team | Implement account and user-management flow | 2026-05-07 | 2026-05-13 | 7 | Complete | Authentication and user-management workflow implemented.
No | Admin capstone CRUD and repository management | Core Feature | Team | Enable admin repository management | 2026-05-08 | 2026-05-15 | 8 | Complete | Admin capstone management implemented and integrated.
No | Sprint 5 | Sprint | Team |  | 2026-06-04 | 2026-06-21 | 18 | Complete
No | Authentication security and validation | Security | Team | Harden authentication inputs and validation | 2026-06-04 | 2026-06-07 | 4 | Complete | Authentication validation and security checks implemented.
No | CSRF protection and role-based decorators | Security | Team | Protect state-changing routes and enforce roles | 2026-06-06 | 2026-06-09 | 4 | Complete | CSRF and authorization decorators implemented.
No | PDF viewer and manuscript request workflow | Core Feature | Team | Support controlled manuscript viewing and requests | 2026-06-09 | 2026-06-15 | 7 | Complete | Protected PDF viewing and request workflow implemented.
No | Authors, adviser, and citation workflow | Core Feature | Team | Connect capstones with authors, advisers, and citations | 2026-06-15 | 2026-06-18 | 4 | Complete | Academic metadata workflow implemented.
No | Core workflow refactoring and bug fixes | Maintenance | Team | Refactor core flow and resolve blocking defects | 2026-06-20 | 2026-06-21 | 2 | Complete | Core workflow refactored and verified.
No | Sprint 6 | Sprint | Team |  | 2026-06-25 | 2026-07-15 | 21 | Complete
No | Security hardening and role synchronization | Security | Team | Synchronize role rules and close access gaps | 2026-06-25 | 2026-07-09 | 15 | Complete | Role handling and access controls hardened.
No | Analytics dashboard and chart interactions | Analytics | Team | Build dashboard metrics and interactive charts | 2026-06-29 | 2026-07-15 | 17 | Complete | Analytics dashboard and interactions implemented.
No | Recycle bin, restore, and archive retention | Archive Management | Team | Implement archive, restore, and retention workflow | 2026-07-11 | 2026-07-13 | 3 | Complete | Archive management workflow implemented.
No | User contact information and profile improvements | Account Management | Team | Improve profile and contact-data handling | 2026-07-15 | 2026-07-15 | 1 | Complete | Profile and contact features implemented.
No | Sprint 7 | Sprint | Team |  | 2026-07-18 | 2026-08-07 | 21 | Needs Review
No | Table, sidebar, and component styling | UI/UX | Team | Refine shared interface components | 2026-07-18 | 2026-07-31 | 14 | Complete | Shared interface styling completed.
No | Database improvements and repository redesign | Development | Team | Refine data model and repository structure | 2026-08-01 | 2026-08-03 | 3 | Complete | Repository and database structure improved.
No | Similarity-analysis and recommendation setup | Data Mining | Team | Establish similarity and recommendation foundation | 2026-08-07 | 2026-08-07 | 1 | Needs Review | Foundation implemented; validation and review still required.
Yes | Sprint 8 | Sprint | Team |  | 2026-08-12 | 2026-08-24 | 13 | Needs Review
No | Data-leak fixes and additional CSRF protection | Security | Team | Close data exposure paths and expand CSRF coverage | 2026-08-12 | 2026-08-19 | 8 | Complete | Security fixes completed for identified exposure paths.
No | Request cancellation, citation, and promotion workflow | QoL | Team | Add request and citation convenience workflows | 2026-08-20 | 2026-08-21 | 2 | Complete | Quality-of-life workflows implemented.
No | Dark mode and responsive/mobile interface | UI/UX | Team | Support dark theme and responsive layouts | 2026-08-22 | 2026-08-23 | 2 | Complete | Dark mode and responsive interface implemented.
Yes | Faculty and Capstone Professor functions | Role Management | Team | Validate faculty-specific role workflows | 2026-08-24 | 2026-08-24 | 1 | Needs Review | Role functions implemented but still require review.
Yes | Sprint 9 | Sprint | Team |  | 2026-08-25 | 2026-09-07 | 14 | In Progress
No | Query and navigation optimization | Performance | Team | Optimize common queries and navigation paths | 2026-08-25 | 2026-08-29 | 5 | Complete | Optimization work completed for targeted paths.
No | Styling, data-leak fixes, and citation-count removal | Maintenance | Team | Resolve UI/security cleanup and remove citation count | 2026-08-25 | 2026-08-30 | 6 | Complete | Targeted maintenance work completed.
Yes | Saved capstones, notifications, and comparison | QoL | Team | Complete saved items, notifications, and comparison flow | 2026-08-31 | 2026-09-04 | 5 | In Progress | Implementation is active and not yet complete.
Yes | Citation exports and database migrations | Development | Team | Finalize export formats and migration scripts | 2026-08-31 | 2026-09-07 | 8 | In Progress | Migration and export work is still in progress.
Yes | PDF extraction for multi-part names | Enhancement | Team | Validate extraction for complex author names | 2026-09-01 | 2026-09-03 | 3 | Needs Review | Implementation requires review and testing.
Yes | Delete confirmation modal and repository icons | UI/UX | Team | Review delete confirmation and repository icon updates | 2026-09-01 | 2026-09-03 | 3 | Needs Review | UI changes require review before completion.
Yes | Topic-similarity layout and empty-state fixes | UI/UX | Team | Finish similarity page layout and empty states | 2026-09-02 | 2026-09-05 | 4 | In Progress | Active UI work; pending completion.
Yes | Dark-theme and error-navigation fixes | UI/UX | Team | Resolve dark-theme and error navigation issues | 2026-09-02 | 2026-09-05 | 4 | In Progress | Active fixes; regression check still pending.
Yes | Security and regression testing | QA | Team | Run security and regression test suite | 2026-08-31 | 2026-09-07 | 8 | In Progress | Testing is underway; unresolved work remains.
Yes | Sprint 10 | Sprint | Team |  | 2026-09-08 | 2026-09-21 | 14 | Not Started
Yes | User acceptance and regression testing | QA | Team | Complete UAT and final regression testing | 2026-09-08 | 2026-09-12 | 5 | Not Started | Planned for final validation sprint.
Yes | Chapter 1, Chapter 2, and system-documentation review | Documentation | Team | Review academic and technical documentation | 2026-09-08 | 2026-09-15 | 8 | Not Started | Planned documentation review.
Yes | Deployment and database-migration verification | Deployment | Team | Verify deployment package and database migration | 2026-09-13 | 2026-09-18 | 6 | Not Started | Planned release-readiness verification.
Yes | Final stakeholder validation and release preparation | Release | Team | Obtain final validation and prepare release | 2026-09-19 | 2026-09-21 | 3 | Not Started | Planned final stakeholder and release work.
Formulas:
Start Date = MIN([Start Date, row below]:[Start Date, row below])
Start Date = MIN([Start Date, row below]:G17)
End Date = MAX([End Date, row below]:[End Date, row below])
End Date = MAX([End Date, row below]:H17)

## Example of Agile Project Plan
Agile Project Plan Template
| Project Name | New Product Launch |  |  | Start Date | End Date | Overall Progress | Project Deliverable | Launch-ready product with core features, documentation, and release plan
| Project Manager | Cyriac Tom |  |  | 2026-01-01 | 2026-02-14 | 83% | Scope Statement | Deliver a stable MVP through three sprints, covering core features, testing, stakeholder review, and launch readiness
At Risk | Task Name | Feature Type | Responsible | Checkpoints | Start | Finish | Duration in days | Status | Comments
No | Sprint 1 | Sprint | Product Team | Sprint Planning Completed | 2026-01-01 | 2026-01-12 | 12 | In Progress | Initial sprint setup and backlog alignment
Yes | Feature 1 | Core Feature | Dev Team | Development Complete | 2026-01-01 | 2026-01-07 | 7 | Complete | Ready for QA validation
No | Feature 2 | Enhancement | Dev Team | Partial Build Done | 2026-01-03 | 2026-01-10 | 8 | On Hold | Waiting for dependency approval
No | Feature 3 | Core Feature | QA Team | Test Cases Prepared | 2026-01-05 | 2026-01-12 | 8 | Needs Review | Requires stakeholder feedback
No | Sprint 2 | Sprint | Product Team | Sprint Review Scheduled | 2026-01-15 | 2026-01-28 | 14 | Approved | Scope and priorities confirmed
No | Feature 4 | Core Feature | Dev Team | Code Review Done | 2026-01-15 | 2026-01-15 | 1 | Complete | Merged into main branch
Yes | Feature 5 | Enhancement | QA Team | Testing Delayed | 2026-01-16 | 2026-01-25 | 10 | Overdue | Blocked due to resource availability
No | Feature 6 | Support Feature | Dev Team | Development Paused | 2026-01-18 | 2026-01-28 | 11 | On Hold | Re-prioritised for next sprint
No | Sprint 3 | Sprint | Product Team | Sprint Review Pending | 2026-01-29 | 2026-02-14 | 17 | Needs Review | Final adjustments required
No | Feature 7 | Core Feature | Dev Team | Build Completed | 2026-01-29 | 2026-02-05 | 8 | Complete | Ready for release testing
No | Feature 8 | Enhancement | QA Team | Regression Testing | 2026-02-01 | 2026-02-08 | 8 | In Progress | Minor issues under review
Yes | Feature 9 | Release Prep | Product + Ops | Go-Live Checklist | 2026-02-05 | 2026-02-14 | 10 | Not Started | Scheduled for final phase
Formulas:
Start Date = MIN([Start Date, row below]:G9)
End Date = MAX([End Date, row below]:H9)

## Dropdown Keys - Do Not Delete -
Dropdown Keys
Yes / No | Priority | Status
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold